## Instructions
Welcome to West Berkshire's Waste Management Strategy Delivery Plan. This plan sets out the activities and actions that the Council along with its partners will undertake to achieve the aims set out in the strategy. Each tab at the bottom of this spreadsheet represents one of our strategic visions and has a list of actions and timescales that fit with each one. Please note that this document is 'live' and as such will be regularly updated to show the Council's progress.

## Increase Recycling Rate
Waste Management Strategy Delivery Plan | [6 empty] | Progress Key: Blue = not started, Green = In progress, on track, Orange= In progress, behind schedule /on hold, Purple = complete |  | Estimated impact on recycling rate: Low: 0-0.9% increase Medium: 1-4.9% increase High: 5%+ increase | Estimated impact on general waste volume: Low: 0-0.9% reduction Medium: 1-4.9% reduction High: 5%+ reduction
Last updated 25.03.2025
Strategic Vision: Increase the districts recycling rate to 60% by 2030
Ref | Actions | Performance Measures | Timescale |  | Responsibility | Comment / Progress | Estimated Impact on Recycling Rate | Estimated Impact on General Waste Volume | Link to Waste Management Strategy Priority | Link to other waste management strategic visions | Linkage to Council Strategy
|  |  | Start | Complete
filter line
RR001 | Implement the Best Practicable Environmental Option to reduce the frequency of black bin collections | Service change implemented | 2025 | TBC | WBC Waste | In progress, on track | High | High | Priority One: Reviewing Collection Services | Make meaningful progress towards halving residual waste to 120kg per person per year by 2042. RW007 | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR002 | Review receptacles provided to residents to present their waste for collection | Options consulted and presented to the leadership for decision | 2026 | 2027 | WBC Waste | In progress, on track | Low/Medium | Low/Medium | Priority One: Reviewing Collection Services | Continue to make West Berkshire a great place to live and work, by minimising the level of litter and detritus. LD009 | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR003 | Consider the implications Simpler Recycling has on the current collection method for collecting recycling | Options consulted and presented to the leadership for decision | 2026 | 2026 | WBC Waste | In progress, on track | Low | Low | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR004 | Continue to work towards phasing out the garden waste collection charge over time | Garden Waste Collection charge phased out. | 2025 | TBC | WBC Waste/Finance | In progress, on track | Medium | Medium | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.9 The green bin charge is being phased out
RR005 | Expand the different types of recyclable materials collected at kerbside, as required by emerging government policies | Increase the items of waste that we collect for recycling in line with Simpler Recycling | 2025 | 2027 | WBC Waste | In progress, on track | Low/Medium | Low/Medium | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR006 | Explore collecting additional materials (such as small electricals) at kerbside | Options considered and presented to the leadership for decision | 2029 | 2031 | WBC Waste | Not started | Low | Low | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR007 | Provide an equivalent level of core service across all property types, including the roll out of a food waste recycling service to flats above shops where practicable | Equivalent services provided to all properties in line with Simpler Recycling requirements. | 2026 | 2027 | WBC Waste | Not started | Low | Low | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR008 | Increase the number of Mini Recycling Centres (MRCs) to collect a range of materials that are not collected kerbside where possible | Increase in the number of MRCs provided across the district Introduce new waste streams for collection at MRCs | 2028 | 2032 | WBC Waste/Property/Planning | Not started | Low | Low | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR009 | Continue to provide guidance for developers and managing agents on communal bin properties | Review the guidance following service changes and relevant regulatory updates. Continue to provide the guidance | 2025 | 2032 | WBC Waste/Planning | In progress, on track | Low | Low | Priority One: Reviewing Collection Services | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RR010 | Continue to deliver waste education programmes at schools across the district and aim to increase the number of education programmes delivered across the district | Review the education programme annualy and following service and relevant regulatory updates. Increase the number of residents engaged year on year. | 2025 | 2032 | WBC Waste | In progress, on track | Low/Medium | Low/Medium | Priority Three: Improve Communication and Community Engagement Regarding Waste Reduction and Recycling | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities
RR011 | Engage with the Town and Parish Councils across the district to see how we can work better together promoting and facilitating awareness of waste reduction and recycling | Discuss options with all town and parish councils | 2027 | 2030 | WBC Waste | Not started | Low | Low | Priority Three: Improve Communication and Community Engagement Regarding Waste Reduction and Recycling | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities
RR012 | Continue to develop a detailed annual communication plan which will outline key topics that would be beneficial to communicate with residents | Production and regular review of plan, incorporating feedback from residents | 2025 | 2032 | WBC Waste | In progress, on track | Low/Medium | Low/Medium | Priority Three: Improve Communication and Community Engagement Regarding Waste Reduction and Recycling | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities
RR013 | Explore enrolling and working with community champions to encourage and promote recycling in their local area | Options consulted and presented to the leadership for decision | 2027 | 2029 | WBC Waste/Communications | Not started | Low | Low | Priority Three: Improve Communication and Community Engagement Regarding Waste Reduction and Recycling | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities
RR014 | Conduct regular reviews of the Council’s website to make it easier for residents to use and ensure the information provided is accessible and easy to understand | Schedule bi-annual review of relevant web pages and ad-hoc reviews during services changes and feedback from residents | 2025 | 2032 | WBC Waste/Digital | In progress, on track | Low | Low | Priority Three: Improve Communication and Community Engagement Regarding Waste Reduction and Recycling | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities

## Halve residual waste
Waste Management Strategy Delivery Plan | [5 empty] | Progress Key: Blue = not started, Green = In progress, on track, Orange= In progress, behind schedule /on hold, Purple = complete |  | Estimated impact on general waste volume: Low: 0-0.9% reduction Medium: 1-4.9% reduction High: 5%+ reduction
Last updated 25.03.2025
Strategic Vision: Make meaningful progress towards halving residual waste to 120kg per person per year by 2042
Ref | Actions | Performance Measures | Timescale |  | Responsibility | Comment / Progress | Estimated Impact on General Waste Volume | Link to Waste Management Strategy Priority | Link to other waste management strategic visions | Linkage to Council Strategy
|  |  | Start | Complete
filter line
RW001 | Continue to work with local charitable organisations and explore how we can increase the amount of bulky items like furniture we can divert for reuse | Options considerd and presented to the leadership for decision | 2025 | 2032 | WBC Waste | In progress, on track | Low/Medium | Priority Two: Minimise Waste and Increase Reuse Priority Nine: Embed Social Value | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW002 | Explore options to expand our reuse provision with an ambition to provide a donation point and/or reuse shop at our Padworth Lane HWRC | Options consulted and presented to the leadership for decision | 2029 | 2032 | WBC Waste | Not started | Low/Medium | Priority Two: Minimise Waste and Increase Reuse | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW003 | Continue to promote reusable nappies through the Real Nappy scheme | Review scheme, implement improvements to increase awareness and uptake | 2025 | 2027 | WBC Waste | In progress, on track | Low | Priority Two: Minimise Waste and Increase Reuse | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW004 | Continue to encourage home composting | Review scheme, implement improvements to increase awareness and uptake | 2025 | 2027 | WBC Waste | In progress, on track | Low | Priority Two: Minimise Waste and Increase Reuse | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW005 | Explore more opportunities to introduce reuse schemes for specific waste types | Options consulted and presented to the leadership for decision | 2029 | 2032 | WBC Waste | Not started | Low/Medium | Priority Two: Minimise Waste and Increase Reuse | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW006 | Explore ways for the Council to support repair initiatives such as “repair cafes” and the “library of things” in the community and through the HWRCs | Options consulted and presented to the leadership for decision | 2029 | 2032 | WBC Waste | Not started | Low/Medium | Priority Two: Minimise Waste and Increase Reuse | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW007 | Implement the Best Practicable Environmental Option to reduce the frequency of black bin collections | Service change implemented | 2025 | TBC | WBC Waste | In progress, on track | High | Priority One: Reviewing Collection Services | Increase the districts recycling rate to 60% by 2030. RR001 | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
RW008 | Formalise and enhance the enforcement of the existing ‘No Side Waste’ and ‘Closed Lid’ policy for general waste “black bins” | Options consulted and presented to the leadership for decision | 2028 | 2029 | WBC Waste | Not started | Low | Priority Three: Improve Communication and Community Engagement Regarding Waste Reduction and Recycling | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres

## Minimise litter and detritus
Waste Management Strategy Delivery Plan | [5 empty] | Progress Key: Blue = not started, Green = In progress, on track, Orange= In progress, behind schedule /on hold, Purple = complete |  | Estimated Impact on Street Scene Low: Maintain Medium: Slightly improve High: Significantly improve
Last updated 25.03.2025
Strategic Vision: Continue to make West Berkshire a great place to live and work, by minimising the level of litter and detritus
Ref | Actions | Performance Measures | Timescale |  | Responsibility | Comment / Progress | Estimated Impact on Street Scene | Link to Waste Management Strategy Priority | Link to other waste management strategic visions | Linkage to Council Strategy
|  |  | Start | Complete
filter line
LD001 | Review the location and capacity of litter bins | Conduct full review of litter bin locations and propose recommendations to improve effectiveness and efficiency | 2025 | 2027 | WBC Waste | In progress, on track | Low/Medium | Priority Five: Improve the Current Recycling, Waste and Street Cleansing Services to Ensure They Help Reduce Litter and Fly-Tipping | N/A | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces
LD002 | Consider increasing the number of recycling bins for on-the-go recycling | Propose options to increase on-the-go recycling | 2028 | 2029 | WBC Waste | Not Started | Low/Medium | Priority Five: Improve the Current Recycling, Waste and Street Cleansing Services to Ensure They Help Reduce Litter and Fly-Tipping | N/A | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
LD003 | Engage with local parish and town councils to see how they can add value to our current litter bin service | Discuss options with all town and parish councils | 2027 | 2030 | WBC Waste | Not Started | Low/Medium | Priority Five: Improve the Current Recycling, Waste and Street Cleansing Services to Ensure They Help Reduce Litter and Fly-Tipping | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities
LD004 | Strengthen our commitment to combat littering and fly-tipping | 1, Increased monitoring by deployment of surveillance techniques across the district 2, Comprehensive public awareness campaign launched 3, Review reporting methods | 2026 | 2029 | WBC Waste | Not Started | Medium | Priority Six: Improve Communication and Enforcement Against Littering and Fly-Tipping | N/A | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces
LD005 | Improve the information available on the Council’s interactive map and online reporting function | Review of current information provided and improvements implemented | 2026 | 2027 | WBC Waste/IT/Digital | Not Started | Low | Priority Six: Improve Communication and Enforcement Against Littering and Fly-Tipping | N/A | OUTCOME: 3.10 Increase education around recycling and its benefits by working with schools and communities
LD006 | Continue to support community-led litter picking initiatives | Work with organisations and local groups to provide necessary litter picking equipment, health and safety support and guidance and promotion of events | 2025 | 2032 | WBC Waste | In progress, on track | Low | Priority Six: Improve Communication and Enforcement Against Littering and Fly-Tipping | N/A | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces
LD007 | Explore the use of innovative technology to help improve the current street scene | Investigate technologies to improve effectives and efficiency of the litter bin and street cleansing service. | 2028 | 2032 | WBC Waste/IT/Digital | Not Started | Low | Priority Six: Improve Communication and Enforcement Against Littering and Fly-Tipping | N/A | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces
LD008 | Explore implementing a ‘No Bins on Streets’ policy for commercial properties | Options consulted and presented to the leadership for decision | 2027 | 2027 | WBC Waste/Highways | Not Started | Low/Medium | Priority Six: Improve Communication and Enforcement Against Littering and Fly-Tipping | N/A | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces
LD009 | Review receptacles provided to residents to present their waste for collection | Options consulted and presented to the leadership for decision | 2025 | 2027 | WBC Waste | In progress, on track | Low/Medium | Priority One: Reviewing Collection Services | Increase the districts recycling rate to 60% by 2030. RR002 | OUTCOME: 1.6 Maintain cleanliness of our streets and other public spaces OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres

## Net Zero
Waste Management Strategy Delivery Plan | [5 empty] | Progress Key: Blue = not started, Green = In progress, on track, Orange= In progress, behind schedule /on hold, Purple = complete |  | Predicted Impact on Carbon Emissions Low: Maintain Medium: Slightly improve High: Significantly improve
Last updated 25.03.2025
Strategic Vision: Reduce Carbon emissions and contribute towards West Berkshire's pledge to be Net Zero by 2030
Ref | Actions | Performance Measures | Timescale |  | Responsibility | Comment / Progress | Predicted Impact on Carbon Emissions | Link to Waste Management Strategy Priority | Link to other waste management strategic visions | Linkage to Council Strategy
|  |  | Start | Complete
filter line
NZ001 | Ensure that the recycling and waste collection fleet is compatible with Hydrotreated Vegetable Oil (HVO) and explore using it in place of diesel | Have all contract fleet vehicles compatible with HVO | 2025 | 2025 | WBC Waste | Completed All food waste trucks currently fuelled with HVO. | Low | Priority Four: Reduce Carbin Emissions Associated with the Collection Services and Improve Air Quality | N/A | OUTCOME: 3.1.West Berkshire Council achieves net zero by 2030, with clear targets and regular independent audits
NZ002 | Continue to investigate the feasibility of using electric and or hydrogen powered vehicles | Options consulted and presented to the leadership for decision | 2028 | 2032 | WBC Waste/Environment Delivery Team | Not started | Medium/High | Priority Four: Reduce Carbin Emissions Associated with the Collection Services and Improve Air Quality | N/A | OUTCOME: 3.1.West Berkshire Council achieves net zero by 2030, with clear targets and regular independent audits
NZ003 | Explore targeting the increased collection and recycling of carbon-intensive materials, such as electrical appliances and textiles | Options consulted and presented to the leadership for decision | 2028 | 2030 | WBC Waste | Not started | Low/Medium | Priority Four: Reduce Carbin Emissions Associated with the Collection Services and Improve Air Quality | N/A | OUTCOME: 3.8 Increased level of waste reused, recycled or composted at home, from public spaces and through our recycling centres
NZ004 | Aspire for the waste service as a whole to be Net Zero by 2030 and carbon negative by 2040 | Measurable improvements implemented to reduce carbon output by waste contract activities, with a plan to achieve carbon negative by 2040 adopted by 2032 | 2025 | 2032 | WBC Waste/Environment Delivery Team | In progress, on track | High | Priority Four: Reduce Carbin Emissions Associated with the Collection Services and Improve Air Quality | N/A | OUTCOME: 3.1.West Berkshire Council achieves net zero by 2030, with clear targets and regular independent audits
NZ005 | Explore the costs and benefits of an alternative fuel for the street cleansing fleet | Options consulted and presented to the leadership for decision | 2028 | 2030 | WBC Waste | Not started | Medium/High | Priority Seven: Reduce Carbin Emissions Associated with the Street Cleansing Service and Improve Air Quality | N/A | OUTCOME: 3.1.West Berkshire Council achieves net zero by 2030, with clear targets and regular independent audits

## Lead the Way
Waste Management Strategy Delivery Plan | [5 empty] | Progress Key: Blue = not started, Green = In progress, on track, Orange= In progress, behind schedule /on hold, Purple = complete
Last updated 25.03.2025
Strategic Vision: Set an example for residents and businesses by improving the Council's own recycling and waste minimisation rates
Ref | Actions | Performance Measures | Timescale |  | Responsibility | Comment / Progress | Predicted Impact | Link to Waste Management Strategy Priority | Link to other waste management strategic visions | Linkage to Council Strategy
|  |  | Start | Complete
filter line
LW001 | Apply the waste hierarchy for Council buildings and at Council events | Waste hierarchy adopted across Council buildings and events | 2026 | 2027 | WBC | Not started | Low/Medium | Priority Eight: Effectively Manage the Council's Own Waste | N/A
LW002 | Apply a criterion for the procurement of goods which embed the waste hierarchy and contribute towards a circular economy | Criterion adopted | 2027 | 2028 | WBC Commissioning/Environment Delivery Team | Not started | Medium | Priority Eight: Effectively Manage the Council's Own Waste | N/A | OUTCOME: 3.7.Residents and businesses contribute to achieve net zero carbon emissions for the District
LW003 | Set up and report on corporate recycling targets | Annual KPI adopted and implemented | 2027 | 2028 | WBC Property/Commissioning | Not started | Low | Priority Eight: Effectively Manage the Council's Own Waste | N/A
LW004 | Embed social value within the delivery of the recycling, waste and street cleansing services contract let | Implement social value as part of the next contract | 2030 | 2032 | WBC Waste/Commissioning | Not started | Medium | Priority Nine: Embed Social Value | N/A
LW005 | Continue to identify and advise businesses that lack a collection contract or are not applying the waste hierarchy | Record and outcome of contact with businesses. | 2025 | 2032 | WBC Waste/Economic Development | In progress, on track | Medium | Priority Ten: Support Local Businesses In Applying the Waste Hierarchy | N/A | OUTCOME: 3.7.Residents and businesses contribute to achieve net zero carbon emissions for the District
LW006 | Explore offering business support and look to embed the principles of this waste management strategy within local businesses and the commercial waste service | Options consulted and presented to the leadership for decision | 2028 | 2029 | WBC Waste/Economic Development | Not started | Medium | Priority Ten: Support Local Businesses In Applying the Waste Hierarchy | N/A | OUTCOME: 3.7.Residents and businesses contribute to achieve net zero carbon emissions for the District

## Sheet3 (hidden)
Actions | Strat Day | Start Month | Start Year | Start Date | End Day | End Month | End Year | End Date | Number of days
Strategic Vision: Increase the districts recycling rate to 60% by 2030 | [8 empty] | 0
Implement the Best Practicable Environmental Option to reduce the frequency of black bin collections | 1 | 4 | 2025 | 2025-04-01 | 1 | 6 | 2025 | 2025-06-01 | 61
Review receptacles provided to residents to present their waste for collection | 1 | 1 | 2025 | 2025-01-01 | 1 | 3 | 2026 | 2026-03-01 | 424
Consider the implications Simpler Recycling has on the current collection method for collecting recycling | 1 | 7 | 2025 | 2025-07-01 | 1 | 3 | 2026 | 2026-03-01 | 243
Continue to work towards phasing out the Garden Waste charge with the ambition to make it free for all households | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Expand the different types of recyclable materials collected at kerbside, as required by emerging government policies | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2027 | 2027-03-01 | 699
Explore collecting additional materials (such as small electricals) at kerbside | 1 | 9 | 2029 | 2029-09-01 | 1 | 3 | 2031 | 2031-03-01 | 546
Provide an equivalent level of core service across all property types, including the roll out of a food waste recycling service to flats above shops where practicable | 1 | 4 | 2026 | 2026-04-01 | 1 | 3 | 2027 | 2027-03-01 | 334
Increase the number of MRCs to collect a range of materials that are not collected kerbside where possible | 1 | 9 | 2028 | 2028-09-01 | 1 | 3 | 2032 | 2032-03-01 | 1277
Continue to provide guidance for developers and managing agents on communal bin properties | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Continue to deliver waste education programmes at schools across the district and aim to increase the number of education programmes delivered across the district | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Engage with the Town and Parish Councils across the district to see how we can work better together promoting and facilitating awareness of waste reduction and recycling | 1 | 4 | 2027 | 2027-04-01 | 1 | 3 | 2030 | 2030-03-01 | 1065
Continue to develop a detailed annual communication plan which will outline key topics that would be beneficial to communicate with residents | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Explore enrolling and working with community champions to encourage and promote recycling in their local area | 1 | 9 | 2027 | 2027-09-01 | 1 | 3 | 2029 | 2029-03-01 | 547
Conduct regular reviews of the Council’s website to make it easier for residents to use and ensure the information provided is accessible and easy to understand | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Strategic Vision: Make meaningful progress towards halving residual waste to 120kg per person per year by 2042 | [8 empty] | 0
Continue to work with local charitable organisations and explore how we can increase the amount of bulky items like furniture we can divert for reuse | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Explore options to expand our reuse provision with an ambition to provide a donation point and/or reuse shop at our Padworth Lane HWRC | 1 | 4 | 2029 | 2029-04-01 | 1 | 3 | 2032 | 2032-03-01 | 1065
Continue to promote reusable nappies through the Real Nappy Scheme | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2027 | 2027-03-01 | 699
Continue to encourage home composting | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2027 | 2027-03-01 | 699
Explore more opportunities to introduce reuse schemes for specific waste types | 1 | 9 | 2029 | 2029-09-01 | 1 | 3 | 2032 | 2032-03-01 | 912
Explore ways for the Council to support repair initiatives such as “repair cafes” and the “library of things” in the community and through the HWRCs | 1 | 4 | 2027 | 2027-04-01 | 1 | 3 | 2029 | 2029-03-01 | 700
Implement the Best Practicable Environmental Option to reduce the frequency of black bin collections | 1 | 4 | 2025 | 2025-04-01 | 1 | 6 | 2025 | 2025-06-01 | 61
Formalise and enhance the enforcement of the existing ‘No Side Waste’ and ‘Closed Lid’ policy for general waste “black bins” | 1 | 4 | 2027 | 2027-04-01 | 1 | 3 | 2028 | 2028-03-01 | 335
Strategic Vision: Continue to make West Berkshire a great place to live and work, by minimising the level of litter and detritus | [8 empty] | 0
Review the location and capacity of litter bins | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2027 | 2027-03-01 | 699
Consider increasing the number of recycling bins for on-the-go recycling | 1 | 4 | 2028 | 2028-04-01 | 1 | 3 | 2029 | 2029-03-01 | 334
Engage with local parish and town councils to see how they can add value to our current litter bin service | 1 | 4 | 2027 | 2027-04-01 | 1 | 3 | 2030 | 2030-03-01 | 1065
Strength our commitment to combat littering and fly-tipping | 1 | 4 | 2026 | 2026-04-01 | 1 | 3 | 2029 | 2029-03-01 | 1065
Improve the information available on the Council’s interactive map and online reporting function | 1 | 4 | 2026 | 2026-04-01 | 1 | 3 | 2027 | 2027-03-01 | 334
Continue to support community-led litter picking initiatives | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Explore the use of innovative technology to help improve the current street scene | 1 | 4 | 2028 | 2028-04-01 | 1 | 3 | 2032 | 2032-03-01 | 1430
Explore implementing a ‘No Bins on Streets’ policy for commercial properties | 1 | 1 | 2027 | 2027-01-01 | 1 | 12 | 2027 | 2027-12-01 | 334
Review receptacles provided to residents to present their waste for collection | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2027 | 2027-03-01 | 699
Strategic Vision: Reduce Carbon emissions and contribute towards West Berkshire's pledge to be Net Zero by 2030 | [8 empty] | 0
Ensure that the recycling and waste collection fleet is compatible with Hydrotreated Vegetable Oil (HVO) and explore using it in place of diesel | 1 | 4 | 2025 | 2025-04-01 | 1 | 4 | 2025 | 2025-04-01 | 0
Continue to investigate the feasibility of using electric and or hydrogen powered vehicles | 1 | 4 | 2028 | 2028-04-01 | 1 | 3 | 2032 | 2032-03-01 | 1430
Explore targeting the increased collection and recycling of carbon-intensive materials, such as electrical appliances and textiles | 1 | 9 | 2028 | 2028-09-01 | 1 | 3 | 2030 | 2030-03-01 | 546
Aspire for the waste service as a whole to be Net Zero by 2030 and carbon negative by 2040 | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Explore the costs and benefits of an alternative fuel for the street cleansing fleet | 1 | 4 | 2028 | 2028-04-01 | 1 | 3 | 2030 | 2030-03-01 | 699
Strategic Vision: Set an example for residents and businesses by improving the Council's own recycling and waste minimisation rates | [8 empty] | 0
Apply the waste hierarchy for Council buildings and at Council events | 1 | 4 | 2026 | 2026-04-01 | 1 | 3 | 2027 | 2027-03-01 | 334
Apply a criterion for the procurement of goods which embed the waste hierarchy and contribute towards a circular economy | 1 | 4 | 2027 | 2027-04-01 | 1 | 3 | 2028 | 2028-03-01 | 335
Set up and report on corporate recycling targets | 1 | 4 | 2026 | 2026-04-01 | 1 | 3 | 2027 | 2027-03-01 | 334
Embed social value within the delivery of the recycling, waste and street cleansing services contract let | 1 | 4 | 2030 | 2030-04-01 | 1 | 3 | 2032 | 2032-03-01 | 700
Continue to identify and advise businesses that lack a collection contract or are not applying the waste hierarchy | 1 | 4 | 2025 | 2025-04-01 | 1 | 3 | 2032 | 2032-03-01 | 2526
Explore offering business support and look to embed the principles of this waste management strategy within local businesses and the commercial waste service | 1 | 4 | 2028 | 2028-04-01 | 1 | 3 | 2029 | 2029-03-01 | 334
Formulas:
Number of days = DAYS([End Date], [Start Date])
Start Date = DATE([Start Year], [Start Month], [Strat Day])
End Date = DATE(Table4[[#This Row],[End Year]],Table4[[#This Row],[End Month]],Table4[[#This Row],[End Day]])